## Job Creation
Job Creation
Strategic Goal 1 |  |  | Attract & Support Business Development
Strategic Goal 2 |  |  | Promote Vocational & Technical Careers
Progress
% done | Goal | Priority | Action Steps | Due By | Lead | Funding Source | Notes
0% | Goal 1 | 1 | Become familiar with all aspects of area resources and programs | 2020-11-30 | Recovery Coordinator | EDA | Assuming hire happens by 9/30 - Will need training by Region 9 & CDC. Ongoing
0% | Goal 1 |  | EDA, Opportunity Zones, Enterprise Zones, OEDIT, Region 9, SBDC, Pueblo Community College
0%
0%
0% | Goal 1 | 2 | Identify business, economic and entrepreneurial rebuild initiative and measures that should be taken to restore economic vitality of affected areas |  | Recovery Coordinator | EDA
0% |  |  | What steps will be taken to accomplish this?
0%
0%
0% | Goal 1 | 2 | Reach out to telecommuters and identify their business needs |  | Broadband Service Office
0%
0%
0%
0% | Goal 2 | 2 | ID and coordinate training resources required for new and expanding businesses |  | Recovery Coordinator | EDA
0%
0% | Goal 1 | 3 | Engage with Innovation Center for business & workforce needs |  | Recovery Coordinator
0%
0%
0% | Goal 2 | 3 | Co-op with Chamber in participating in school career days and workforce development |  | Mary Jo/Kym LeBlanc Esparza
0%
0%
0% | Goal 2 | 3 | Engage with SW Colorado Workforce Center to identify training resources |  | Mary Jo/Kym LeBlanc Esparza/Sally High
0%

## Community Enhancement
Community Enhancement
Strategic Goal 1 |  |  |  | Engage with Community Organization & Gov't Entities to Support ED Efforts and ECO DEVO Infrastructure
Strategic Goal 2 |  |  |  | Engage with Economic Policy
Progress
% done | Goal | Priority | Action Steps | Due By | Lead | Funding Source | Notes
0% | Goal 1 | 1 | Work with Broadband Service office to identify business needs and expand SCAN fiber lease options | end of 2021 | Broadband Service Office | T/C | strategic plan due by February, DoLA grant by July 2021
0%
0%
0%
0% | Goal 1 | 1 | Participate in the Economic Recovery Task Force and assist with implementing action plans | ongoing | Recovery Coordinator | EDA | lead on 5-Star program, scheduling sector-focused meetings
0%
0%
0%
0% | Goal 1 | 1 | Include regular economic driver topics in monthly BOD meetings to encourage public discussion of ideas concerning economic activity | ongoing | Mary Jo/Robert |  | Jan-strat plan; Feb-BB;
0%
0%
0%
0% | Goal 1 | 2 | Expand information and input from entities focused on the community’s economic health |  | CDC Board
0%
0%
0%
0% | Goal 2 | 3 | Undertake independent research of relevant resources, seek input from public, facilitate discussion of specific issues of current interest |  | Recovery Coordinator
0%
0%
0%
0% | Goal2 | 3 | Adopt positions on public issues that objectively considers the diverse interest relevant to CDC mission | ongoing | CDC Board

## Economic Outreach
Economic Outreach
Strategic Goal 1 |  |  |  | Lead Community Conversations to Address Emerging and Current Issues & Priorities
Strategic Goal 2 |  |  |  | Inspire Public Confidence & Understanding of the CDC's Mission & Deliverables
Progress
% done | Goal | Priority | Action Steps | Due By | Lead | Funding Source | Notes
0% | Goal 1 | 1 | Assist community leaders, business owners and residents in gaining access to state and federal programs designed to assist with economic revitalization as requested | Ongoing all year | Chamber, Region 9, SBDC
0%
0%
0%
0% | Goal 1 | 2 | Help community identify and fill in economic development core area gaps so that business recruitment can occur |  | Recovery Coordinator | EDA
0%
0%
0%
20% | Goal 1 | 3 | Participate in regional/state economic forums and share information with our community | Ongoing all year | CDC |  | attended : SW Eco Forum, SBDC/PSCOC PPP2.0 and community grant opportunities
0%
0%
0%
10% | Goal 2 | 1 | Celebrate and acknowledge wins for individuals and organizations |  | Mary Jo/Robert |  | acknowledge MJC as Ed Morlan ED leader award
0%
0%
0%
0% | Goal 2 | 2 | Host monthly informational gatherings such as Topic-Based Happy Hours or Morning Coffee | On Hold
0%
0%
0%
0% | Goal2 | 3 | Coordinate committee events and trainings as applicable |  | Robert/Mary Jo

## Maximize CDC Resources
Maximize CDC Resources
Strategic Goal 1 |  |  |  | Secure Funding to Facilitate Increased Direct Services
Strategic Goal 2 |  |  |  | Promote the CDC's Value Proposition
Progress
% done | Goal | Priority | Action Steps | Due By | Lead | Funding Source | Notes
25% | Goal 1 | 1 | Hire Economic Development Director | completed | Region 9 & CDC Board | EDA secured 1.5 yrs | Start with Eco Devo Recovery Coordinator
100% | Goal 1 |  | Write job description and post RFP |  | Laura Marchino and Mary Jo
0%
0%
0% | Goal 1 | 1 | Actively pursue new CDC membership and engage members to invite other successful businesses to our membership | ongoing | Recovery Coordinator | EDA | ERC not major focus right now
0%
0%
0%
0% | Goal 1 | 2 | Explore and pursue volunteers, investors, business owners, partnerships and grants
0% |  |  | Community feels that CDC does not do enough for the business community - how do we communicate what we do? |  | Recovery Coordinator
0%
0%
0% | Goal 1 | 3 | Provide enhanced opportunities for socializing among members and for community economic networking by adding social component to regular CDC events and activities | On Hold
0%
0%
0%
0% | Goal 1 | 3 | Seek membership among underserved community groups, retirees, home commuters who lack opportunities for interactions with others having shared interest |  | Recovery Coordinator | EDA
0%
0%
0%
0% | Goal 2 | 1 | Develop marketing strategy |  | Recovery Coordinator | EDA
0%
0%
25% | Goal 2 | 2 | Maximize use of CDC website, Facebook, e-newsletters, and other relevant media |  | Recovery Coordinator/Mary Jo | EDA